SATHYABAMA INSTITUTE OF SCIENCE AND TECHNOLOGY • AWS STUDENT BUILDER GROUP KAIROS 2027 (GRAND EDITION) Corporate Sponsor Benefit Fulfillment Matrix & Proof-of-Performance (PoP) Checklist Comprehensive Quality Assurance, Ground Operations & Post-Event ROI Protocol DIRECT ACCOUNTABILITY: NIKKI (CPFO) ¦ PRINT FREEZE: DEC 20, 2026 ¦ PROOF OF PERFORMANCE (PoP) PROTOCOL ¦ POST-EVENT ROI DOSSIER SLA: 7-10 DAYS

★ OPERATIONAL FULFILLMENT MANDATE This document ensures 100% compliance with every benefit promised to corporate partners in signed MoUs. It details asset ingestion specifications, pre-event verification gates, on-site photography assignments for proof-of-performance (PoP), and delivery standards for the post-event ROI dossier. No sponsor promise is left unfulfilled.

1. Master Fulfillment Tracking Matrix

Operational tracking table monitoring deliverable readiness across signed and pipeline partners:

| Sponsor Entity | Committed Tier | Contract Value | Logo Ingested? | Backdrop & Standees? | LED Wall Ready? | Keynote Slated? | Live Stream Video? | Resume DB Dispatched? | Escrow Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Amazon Web Services (AWS) | Title Partner | ₹2,00,000 + $50k Credits | [x] SVG Approved | [ ] In Layout | [x] Ready (Center) | Day 1: 11:15 AM (20m) | [x] 30s Cued | [ ] Post-Qualifier | [ ] Pending Signoff |
| Presidio Cloud Solutions | Co-Powered By | ₹1,00,000 | [ ] EPS Requested | [ ] In Layout | [ ] Queued | Day 1: 11:35 AM (10m) | [ ] 15s Needed | [ ] Post-Qualifier | [ ] Pending Signoff |
| Zoho Corporation | Co-Powered By | ₹1,00,000 | [ ] SVG Requested | [ ] In Layout | [ ] Queued | Day 2: 02:00 PM (10m) | [ ] 15s Needed | [ ] Post-Qualifier | [ ] Pending Signoff |
| Freshworks | Track Partner (AI) | ₹25,000 | [ ] PNG Requested | [ ] Track Strip | [ ] Queued | Track Briefing (5m) | [ ] Lower-Third | [ ] Post-Event | [ ] Pending Signoff |
| Red Bull India | Official Energy | In-Kind (2k Cans) | [x] Vector Approved | [x] Sampling Mapped | [x] Station Crest | Midnight Shoutout | [ ] Lower-Third | N/A | [x] Confirmed |
| JetBrains | Tooling Partner | 500 Dev Licenses | [x] Logo Approved | [x] Swag Table | [x] Partner Slide | Opening Mention | [ ] Lower-Third | N/A | [x] Vouchers Ingested |

2. Asset Ingestion Specifications & Technical QA

All creative collateral must adhere strictly to these technical standards to prevent visual degradation:

| Asset Type | Dimensions & Resolution | Color Profile & Format | Quality Acceptance Threshold |
| --- | --- | --- | --- |
| Corporate Vector Logo | Scalable Vector / 300 DPI Transparent PNG | RGB + CMYK (SVG, EPS, AI) | Must include dark-mode and light-mode variants; no pixelation at 10ft scale |
| Main Stage LED Wall Asset | 3840 × 1920 px (16:9 Widescreen) | RGB 72–150 DPI (PNG / PSD) | Obsidian-black background; centered crest for Title, flanking for Co-Powered |
| Stage Backdrop Banner | 20 feet wide × 10 feet high | CMYK 300 DPI (TIFF / PDF Vector) | 35% surface for Title, 20% for Co-Powered, shared footer for Associate |
| Rollup Standees (16 Total) | 6 feet high × 3 feet wide (16 units) | CMYK 150–300 DPI (Vinyl Flex) | Title on all 16 standees; Co-Powered on 10; Track on dedicated standee |
| Apparel Crest (Hoodies & Tees) | 12 inches wide (Front) / 10 inches (Back) | CMYK Vector (AI / EPS) | Single or two-tone screen print; strictly vector paths |
| Live Stream Video Commercial | 1920×1080p 60fps / 3840×2160p 4K | MP4 H.264 / AAC Audio | Title: 30 seconds broadcast every 2h; Co-Powered: 15 seconds every 4h |

3. Pre-Event Verification Gates & Deadlines

Fulfillment operates across four strict quality verification checkpoints:

Gate 1 (D-45 / December 10, 2026): Vector Asset Freeze: All sponsor logos, vector paths, and brand guidelines must be signed off and archived in the master asset drive.

Gate 2 (D-30 / December 20, 2026): Hard Print Freeze: Backdrops, 16 standees, 110 hoodies, 550 tees, and 650 lanyards sent to vendors. No logo modifications permitted after this gate.

Gate 3 (D-15 / January 07, 2027): Keynote & Jury Signoff: Executive speaker titles, bios, headshots, and nominated jury members confirmed and integrated into master schedule.

Gate 4 (D-5 / January 17, 2027): Technical Media & Live Stream QA: Video commercials cued into OBS broadcast system; foyer booth spaces marked with power sockets and table signage.

4. On-Site Proof of Performance (PoP) Protocol

Corporate sponsors require tangible evidence that every contracted deliverable was executed. The Media & Photography Squad (Division 5) is assigned to capture the following five mandatory DSLR proof assets:

1. Executive Keynote on Stage: High-res wide and tight shots of the corporate executive speaking on the main auditorium stage with an attentive audience of 500+ builders.

2. Stage LED Wall & Backdrop Brand Prominence: Clear, unobstructed photos showing the sponsor's logo glowing on the 3840×1920 LED Wall behind speakers and winners.

3. Foyer Exhibition Lounge & Hacker Engagement: Dynamic photos of students crowding around the corporate kiosk, interacting with reps, testing demos, and receiving merchandise.

4. Apparel & Smart Badge Close-Ups: Macro photography of participants actively coding while wearing hoodies, jerseys, and custom jacquard lanyards bearing the sponsor's crest.

5. Jury Evaluation & Mentorship Sessions: Documenting corporate evaluators reviewing finalist projects at hacker bays during Milestone Checkpoints.

★ LIVE BROADCAST VERIFICATION SLA Broadcast Logging SLA: The Live Stream Crew must maintain a digital timestamp log recording every instance a corporate video commercial or lower-third graphic is aired on the 48-hour global YouTube/LinkedIn broadcast.

5. Post-Event 10-Slide Sponsor ROI Dossier Standard

Within 7 to 10 business days following the Grand Finale (no later than February 05, 2027), the Sponsorship Squad delivers a comprehensive 10-slide executive ROI dossier to the corporate sponsor's leadership team:

| Slide No. | Slide Topic & Content | Key Metrics & Evidence Included |
| --- | --- | --- |
| Slide 1 | Executive Cover & Gratitude | Formal thank you letter from President Thenappan T and Dean School of Computing |
| Slide 2 | National Reach & Applicant Telemetry | 2,000+ applicants, geographic map across 20+ states, top colleges represented |
| Slide 3 | Finalist Demographics & Quality | 100 elite teams, gender ratio, tech stack distribution (AI, Cloud, Web3) |
| Slide 4 | Main Stage & Keynote Highlights | Keynote address photos, crowd reaction metrics, VIP jury participation |
| Slide 5 | Ground Brand Immersion Proofs | Photos of LED Wall, 20x10ft backdrop, 16 standees, and foyer demo kiosk crowds |
| Slide 6 | Apparel & Collateral Integration | Photo evidence of 110 hoodies, 550 tees, 650 lanyards, and smart badges |
| Slide 7 | 48-Hour Live Broadcast Metrics | Live stream view count, peak concurrent viewers, global watch-time analytics |
| Slide 8 | Digital & Social Media Reach | 500,000+ digital impressions, Instagram/LinkedIn engagement rates, top posts |
| Slide 9 | Track & Challenge Outcomes | Overview of student prototypes built using sponsor APIs/models; winner highlights |
| Slide 10 | Talent Access & Partnership Renewal | Dispatch confirmation of verified resume database + invitation to renew for Kairos 2028 |

★ RETENTION & RENEWAL STRATEGY Delivering a flawless post-event ROI dossier is our single most effective sales tool for Kairos 2028. Sponsors who receive prompt, professional documentation renew their partnerships at higher tiers with zero friction.